## Project Planner
Project Timeline
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| Task | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Initial Brainstorming | 1 | 5 | 1 | N/A | 0%
| One Page GDD | 5 | 5 | N/A | N/A | 0%
| PowerPoint Pitch | 10 | 5 | N/A | N/A | 0%
| Get Approval/Tweak | 15 | 5 | N/A | N/A | 0%
D | Full Design Document | 20 | 5 | N/A | N/A | 0%
| Technical Design Document | 25 | 5 | N/A | N/A | 0%
| Characters | 30 | 5 | N/A | N/A | 0%
| Levels | 35 | 5 | N/A | N/A | 0%
| Obstacles | 40 | 5 | N/A | N/A | 0%
| Powerups | 45 | 5 | N/A | N/A | 0%
| AI | 50 | 5 | N/A | N/A | 0%
| Art Design Document | 55 | 5 | N/A | N/A | 0%
| Make Changes | 60 | 5 | N/A | N/A | 0%
| Game Development | 65 | 5 | N/A | N/A | 0%
| Level Programming | 70 | 5 | N/A | N/A | 0%
| Character Programming | 75 | 5 | N/A | N/A | 0%
| AI Programming | 80 | 5 | N/A | N/A | 0%
| Beta Testing | 85 | 5 | N/A | N/A | 0%
| QA Testing | 90 | 5 | N/A | N/A | 0%